## sprint4
# | task | Owner | Start Date | End Date | Status | Comments
1 | QA Regression Testing | jessie | 2020-04-20 | 2020-05-09 | complete | 1) 4 uses cases (besides FGPO), 2) test happy paths and exceptions, 3) document outcomes and logs
2 | debug | isoftstone dev team | 2020-05-01 | 2020-05-09 | complete
3 | submit CR | David | 13th 11am
4 | approve cr | ravinder | 14th 2pm
5 | release note | David | 13th 11am
8 | Deployment of Packages to Production | ravinder, isoftstone dev team | 2020-05-15 |  |  | package, library, asset excel, release note will be shared
9 | publish package | isoftstone Dev team | 2020-05-15
10 | upload package | ravinder
11 | upload /deploy process | ravinder
12 | publish library | isoftstone Dev team | 2020-05-15
13 | upload library | ravinder
14 | Setting up asset, | ravinder
15 | Testing Data-/prod/smoke/ | David
16 | Prod somoke testing | jessie+isoftstone dev team |  |  |  | 1) mainly on 5 uses cases , 2) test happy paths for masterscript as well , 3) setup test data, 4) document outcomes and logs. Manual smoke testing FGPO Note: There are ecV and VAT UI differences between QA and production versions.
17 | job and schedule in Production | jackson |  |  |  | use new scheudle for master script and new access,, off board.
18 | SN possible impact | Reto |  |  |  | SN upgrad in UAT
19 | row back | isoftstone Dev team |  |  |  | roll back old version if issue occurs
deployment start 14th 3:30pm, until end of day 15th

## QA
Sprint 4 Proposal
Details of regression testing QA
Case Name | Start Date | End Date | testing status | NOTE:
Style Group request
Product Segmentation request
Silhouette request
Attitude request
DDPUpdate | 2020-05-05 | 2020-05-08 | completed
MontlyReport
PasswordReset | 2020-05-05 | 2020-05-08 | completed
StyleNameChange | 2020-05-05 | 2020-05-08 | completed
SeasonRefresh
New Collection/New SubCollection request | 2020-04-20 | 2020-04-28 | completed
New Collection/Existing SubCollection request | 2020-05-01 | 2020-05-09 | completed
Existing Collection/New SubCollection request | 2020-05-05 | 2020-05-09 | completed
New collection/none subcollection request new request | 2020-05-06 | 2020-05-08 | completed
Existing Collection/Existing SubCollection request | 2020-04-29 | 2020-05-05 | completed
Material request
ClassSubClass
Off_Board_Request | 2020-04-23 | 2020-05-08 | block | testing depending on access request
WeeklyReport
AccessRequest | 2020-04-23 | 2020-05-08 | block | egnyte does not syncy with sharefolder , ticket create for icident.
reframe | 2020-05-05 | 2020-05-08 | completed
Fiscal year
FGPO

## Prod
Smoke testing Production
Case Name | assign | start date | end date | Note
Style Group request
Product Segmentation request
Silhouette request
Attitude request
DDPUpdate
MontlyReport
PasswordReset
StyleNameChange
SeasonRefresh
New Collection/New SubCollection request
New Collection/Existing SubCollection request
Existing Collection/New SubCollection request
New collection/none subcollection request
Existing Collection/Existing SubCollection request
Material request
ClassSubClass
Off_Board_Request
WeeklyReport
AccessRequest
MasterScript
Fiscal year
FGPO | Sue
Release schedule proposol-production
Realse Name
release 1
release 2

## Sheet1
- General Master Script (AUI-253, AUI-254, AUI-255)
- FGPO Use Case (AUI-264, AUI-321, AUI-322)
o Implementation of New Overall Reprocess Use Case on open PO’s in ecVision.
- Style Rename (AUI-319)
o Adjustment of end user contact and completion notification.
- DDP Update (AUI-315)
o Modification of prior acceptance criteria on approvals
- Collection/Sub-Collection (AUI-263, AUI-290, AUI-289, AUI-288)
o Enhanced validation and business exception handling.
- Offboard Request (AUI-258)
o Enhanced end user communication upon completion.
- New Access Request (AUI-259)
o Updated end user communication format.